## March
Cold work Permit No. | Hot Work Permit No | Issued for Day = 1 | Work Description | Date issued | Module Number | Area Authority | Date Completed | SSIC | EPM | ESEC | Lock Out Box No | work continuing under Permit No
42832 |  | 0 | INSTALL , REMOVE BOTTOM SPOOL,SHEAVE overboard by rope access | 2015-02-13 | riser balcony | Prod | 2015-03-07
43022 |  | 0 | Remove thermowell for inspection CO2 Comp B | 2015-02-15 | 73 | prod |  |  | 936 |  | 4
43115 |  | 0 | Repair leaks on P3 hydraulics Group 2 network | 2015-02-13 | riser balcony | Prod |  |  | 43312 |  | 12
43124 |  | 0 | connection ROV hook | 2015-02-15 | riser | prod | 2015-03-07
43013 |  | 0 | scaffold operations | 2015-02-18 | Topsides&main deck | prod | 2015-03-04
7321 |  | 0 | Carry out repairs on Cargo Pump LCV positioner | 20/02/15 | Pump Room | Cargo
42987 |  | 0 | Preparation for pull in SPH-8 (Production removable spool) | 22/02/15 | riser balcony | prod | 2015-03-09 |  | 43325 |  | 8
42989 |  | 0 | Liffting / rigging material certification by 3rd party | 22/02/15 | main deck | cargo | 2015-03-02
| 35003 | 0 | Use of camera | 22/02/15 | topsides | prod
42844 |  | 0 | Monthly inspection of fire foam monitors | 22/02/15 | topsides | prod | 2015-03-02 | 267
42988 |  | 0 | Preperation for Pulling SPH-8 Gas Lift Spool | 23/02/15 | Riser Balcony | prod | 2015-03-08 |  | 43323 |  | 15b
42913 |  | 0 | Scaffold operations | 24/02/2015 | topsides | prod | 2015-03-02
| 2576 | 0 | Trouble shooting calibration checks on OCM | 24/02/2015 | 68 | cargo | 2015-03-02
42910 |  | 0 | Manual Cargo handling | 24/02/2015 | topsides | prod
43146 |  | 0 | Install and remove bottom spool sheave ROV hook | 23/02/2015 | Riser balcony | prod | 2015-03-09
42916 |  | 0 | Take Gas Samples | 24/02/2015 | 77 / 74 | prod |  | 272
42915 |  | 0 | Pump Room Entry | 24/02/2015 | pump room | cargo |  |  |  | 42915/1
| 35012 | 0 | Troubleshooting MGC A #1 Inlet throttle valve - PCV1124 | 24/02/2015 | 71 | prod | 2015-03-06
42917 |  | 0 | Rescue boat inspection and maintenance | 24/02/2015 | FRC | cargo | 2015-03-05 | 273
| 34643 | 0 | Loop Checking on CO2 Comp A | 25/02/15 | 73 | prod | 2015-03-04 |  | 937 |  | 14b
42908 |  | 0 | Lube oil flushing in refrig comp A | 25/02/15 | 74 | prod | 2015-03-04
42909 |  | 0 | Lube oil flushing in refrig comp B | 25/02/15 | 74 | prod | 2015-03-04
42994 |  | 0 | Lube oil flushing of CO2 Comp A | 25/02/15 | 73 | prod
42916 |  | 0 | to take gas sample | 25/02/15 | 63 | prod | 2015-03-03
7324 |  | 0 | Secure loose pipe clamp on pancake | 25/02/15 | 267 | prod | 2015-03-04
7336 |  | 0 | Electrical repairs in ER | 26/02/15 | ER | maint | 2015-03-04
7337 |  | 0 | Preservation on electrical motors on topsides | 26/02/15 | topsides | prod | 2015-03-04
7335 |  | 0 | electrical repairs in accom | 26/02/15 | accom | cargo | 2015-03-04
42930 |  | 0 | Dive operations | 26/02/15 | riser balcony | prod | 2015-03-04 |  | 40620 |  | 3
43066 |  | 0 | Installation of tubing and rotate flushing ring on CO2 Membrane C Condensate leg | 26/02/15 | 78 | prod | 2015-03-03 |  | 324 |  | 1
7334 |  | 0 | Weekly amos routines on cranes | 26/02/15 | cranes | cargo | 2015-03-04
43047 |  | 0 | Energise welding socket #7 | 26/02/15 | 21 | prod | 2015-02-26
| 2587 | 0 | Electrical repairs on Topsides and main deck lighting | 26/02/15 | topsides | prod | 2015-03-04
| 2581 | 0 | Trouble shoot cargo valve malfunction | 26/02/15 | main deck | cargo | 2015-03-04
43111 |  | 0 | Test Interlock sequence function test pigging operations | 26/02/15 | 267 / 266 | prod | 2015-03-06
| 2588 | 0 | To Carry out proving on mod 68 | 26/02/15 | 62 68 | prod | 2015-03-04 |  | 337 / 339 |  | 10
43073 |  | 0 | leak repair on IGC A pipe work and flanges as per attached P&ID | 26/02/15 | 76 | prod | 2015-03-09
7322 |  | 0 | Carry out checks on the Vessel HV Transformers - TF4315B | 26/02/15 | ER | maint | 2015-03-04 |  | 274 |  | ?
42933 |  | 0 | Repair leaks on seal gas panel of IGC B | 26/02/15 | 76 | prod | 2015-03-05
7338 |  | 0 | General repairs in accomodation and gully | 27/02/15 | accom | cargo | 2015-03-05
| 35014 | 0 | Check and calibrate instrumentation on MGC B #1 | 27/02/15 | 72 | prod | 2015-03-10 | 284
42914 |  | 0 | Running of baur marine compressor to charge air cylinders | 27/02/15 | accom | cargo | 2015-03-06
| 34645 | 0 | Calibration on Mol seive #4 PDT | 27/02/15 | 74 | prod | 2015-03-06 |  | 340 |  | 6
| 35005 | 0 | Camera | 27/02/15 | topsides | prod | 2015-03-05
43074 |  | 0 | Repair coupling guard loob oil leak on MGC B #1 | 27/02/15 | 72 | prod | 2015-03-02 |  | 40625 |  | 13a
42997 |  | 0 | Pulling SLWR I-Tube 17 including removal of rigging and pulling head | 28/02/15 | Riser balcony | prod | 2015-03-04
| 35015 | 0 | Check the parameters of T71LST5104 on MGC B #2 | 28/02/15 | 72 | prod | 2015-03-04 | 35015
42944 |  | 0 | to install a blind flange on the center drain box at mod 22 | 28/02/15 | mod 22 | prod | 2015-03-02
4019 |  | 0 | Rust removing and painting in ER | 28/02/15 | ER | maint | 2015-03-04
42936 |  | 0 | Conduct replacement of opening lever mechinism for circuit breaker - SRP Pump B | 28/02/15 | ENIF | UEA | 2015-03-02 |  | 1480 |  | 28
42935 |  | 0 | Conduct replacement of opening lever mechinism for circuit breaker - SRP Pump A | 28/02/15 | ENIF | UEA | 2015-03-02 |  | 1470 |  | 28
4021 |  | 0 | Rope access operations in ER | 2015-03-01 | ER | maint
42949 |  | 0 | Setting up IKM Equipment on Mod 78 & 267 | 2015-03-01 | 78 | prod | 2015-03-06
43152 |  | 0 | Install Missing flap pin in pig detector - non intrusive | 2015-03-01 | 267 | prod | 2015-03-08
43072 |  | 0 | Replace defective lighting on LG for Pre Treater | 2015-03-01 | 62 | prod | 2015-03-02
43162 |  | 0 | Tubing instalation for analyzer - CO2 membranes | 2015-03-01 | 78 | prod | 2015-03-08
43151 |  | 0 | rope access operations on topsides | 2015-03-01 | topsides | prod | 2015-03-06
| 2593 | 0 | General hotwork in the workshop | 2015-03-01 | workshop | cargo | 2015-03-07
| 34666 | 0 | conductivity and continnity tests by petrobras | 2015-03-01 | riser balcony | prod | 2015-03-02
43152 |  | 0 | Run compressors with SSIC in place (overides) | 2015-03-01 | 72, 71 , 76 | prod | 2015-03-02 | 789 / 281 |  |  |  | CWP43197
43161 |  | 0 | Perform pressure testing of outstanding tubing on mod 73 (CO2 comp A & B) | 2015-03-01 | 73 | prod | 2015-03-08 |  | 342 |  | 7 | CWP43198
43171 |  | 0 | Cleaning of drain boxes | 2015-03-01 | topsides | prod | 2015-03-06
42921 |  | 0 | Replace lighting fixtures in accom (EX) | 2015-03-01 | Accom | cargo | 2015-03-03 |  | 1235 |  | 13a
42942 |  | 0 | Install tuning software on EWS | 2015-03-01 | CCR | prod | 2015-03-07
42950 |  | 0 | Commissioning of subsea control system by One Subsea | 2015-03-01 | ENIF | UEA | 2015-03-08
43050 |  | 0 | replacement of cargo pump room vent fan | 2015-03-01 | main deck | cargo | 2015-03-02
| 34664 | 0 | check & repair fault temp transmiter on MGC B #2 | 2015-03-01 | 72 | prod | 2015-03-09
| 34651 | 0 | Repairs to leak on IGC A (non intrusive) | 2015-03-01 | 76 | prod | 2015-03-07 |  | 43332 / 40631 /40634 /43335 |  | 17a
| 2589 | 0 | Functional checks F&G on mod 78 | 2015-03-01 | 78 | prod | 2015-03-04 | 149 / 150 / 466
42946 |  | 0 | Clean up lube oil CO2 Comp B | 2015-03-02 | 73 | prod | 2015-03-07
42947 |  | 0 | Clean up lube oil CO2 Comp A | 2015-03-02 | 73 | prod | 2015-03-07
| 35023 | 0 | Running IKM N2/He equipment | 2015-03-02 | fwd laydown | prod | 2015-07-03
| 35028 | 0 | fault finding on control of GT#4 | 2015-03-02 | mod 11 | maint | 2015-02-03
43201 |  | 0 | Take oil sample on P2 | 2015-03-02 | 267 | prod | 2015-08-03
42996 |  | 0 | Divinf operations | 2015-03-02 | Riser balcony | prod | 2015-08-03
7340 |  | 0 | Carry out monthly calibration routines on O2 analyzer on N2 Gen | 2015-03-02 | ER | maint | 2015-02-03
7339 |  | 0 | Carry out monthly calibration routines on O2 analyzer on IG System | 2015-03-02 | ER | maint | 2015-02-03
43163 |  | 0 | Scaffolding operations | 2015-03-02 | topsides | prod | 2015-08-03
| 35026 | 0 | Measuring conductivity of paint on CPVC Pipe for chlorine injection | 2015-03-02 | main deck | prod | 2015-07-03
7341 |  | 0 | Fault finding and repair of elevator | 2015-03-02 | accom | cargo | 21/3/15
| 34646 | 0 | Check and calibrate level transmitter on IGC A | 2015-03-02 | 76 | prod | 2015-03-10 | 281
| 34652 | 0 | Carry out modification on hydraulic panel on Test Manifold HIPPS Valves (Hydraulics) | 2015-03-02 | 266 | prod | 2015-04-03 |  | 43333 |  | 11
4753 |  | 0 | Install new foam pump (foam Pump A) | 2015-03-02 | foam room | cargo | 2015-03-02 | 301 | 1294 |  | 4a
7331 |  | 0 | Loop checks on offload sdv | 2015-03-02 | Poop deck | cargo | 2015-04-03
43212 |  | 0 | Contact replacement of opening lever mechanism - MGC B #2 | 2015-03-02 | ENIF | prod |  |  | 280 |  | 4a
43205 |  | 0 | Contact replacement of opening lever mechanism - MGC A #1 | 2015-03-02 | ENIF | prod |  |  | 279 |  | 9a
| 34667 | 0 | To check and repair flow transmiter T71FT1173 in MGCA T1 | 2015-03-02 | 71 | prod | 2015-06-03
43174 |  | 0 | Topping up IKM Generaor with diesel | 2015-03-02 | 78 | prod | 2015-09-03
7329 |  | 0 | Remove turbine meter and spool piece for prover run | 2015-03-03 | 68 | prod | 2015-04-03
| 2594 | 0 | Carry out calibration checks on O2 Analyzer PSA N2 analyzer | 2015-03-03 | 79 | prod | 2015-04-03
42943 |  | 0 | Isolation of dry gas seal on CO2 Comp Train A | 2015-03-03 | 73 | prod | 2015-08-03 |  | 937 |  | 14a
43217 |  | 0 | Take PVT sample P2 | 2015-03-03 | 63 | prod | 2015-03-03 | 43217
| 34655 | 0 | Carry out modification on hydraulic panel for Production HIPPS SDV's | 2015-03-03 | 266 | prod | 2015-04-03 |  | 43336 |  | 11
43207 |  | 0 | Canduct repair of lever mechanism - GT3 | 2015-03-03 | ENIF | UEA | 2015-03-03 |  | 284 |  | 11
43204 |  | 0 | Canduct repair of lever mechanism - GMGC B #1 | 2015-03-03 | ENIF | UEA | 2015-03-03 |  | 40633 |  | 17
43203 |  | 0 | conduct replacement of opening lever mechanism for HD4 circuit braker IGC A | 2015-03-03 | ENIF | UEA | 2015-03-03
43213 |  | 0 | conduct replacement of opening lever mechanism for HD4 circuit braker IGC B | 2015-03-03 | ENIF | UEA | 2015-03-03
4752 |  | 0 | install new foam pump | 2015-03-03 | foam pump room | cargo | 2015-03-03
| 35030 | 0 | Proving operation of 12"rundown meter | 2015-03-04 | 68 | prod | 2015-03-10 |  | 337 / 339 |  | 10
43181 |  | 0 | DCS updates as per DCF | 2015-03-04 | CCR | prod | 2015-08-03
| 34647 | 0 | Check and calibrate level transmitters on IGC B | 2015-03-04 | 76 | prod | 2015-03-10 | 291
43218 |  | 0 | Pump Room Entry | 2015-03-04 | Pump Room | cargo | 2015-10-03 |  |  | 43218/1
43220 |  | 0 | Pipe alignement on CO2 compressor Train B | 2015-03-04 | 73 | prod | 2015-09-03 |  | 936 |  | 11a
43175 |  | 0 | Manual cargo handling | 2015-03-04 | all areas | cargo | 2015-10-03
| 2590 | 0 | Carry out F&G Test of gas detectors | 2015-03-04 | 74 | prod | 2015-07-03 | 468 / 467 / 469 / 470
4023 |  | 0 | Remove oily bilge pump valve box for inspection | 2015-03-04 | ER | maint | 2015-10-03 |  | 051 / 40651 |  | 4a
| 35033 | 0 | Fault find on limit switch indication of fuel valve of GT3 | 2015-03-04 | ENIF | prod | 2015-06-03
4025 |  | 0 | Tighten rudder locking arrangement | 2015-03-04 | ER | maint | 2015-08-03
| 34656 | 0 | To install new cam and cam valve on the actuator of T74-SDV-6908 | 2015-03-04 | 63 | prod | 2015-04-03
| 35031 | 0 | To investigate and trouble shooting of T71FCV1176 on MGC A T1 | 2015-03-04 | 71 | prod | 2015-04-03
7343 |  | 0 | AMOS routines on lifeboats | 2015-03-05 | 471 | cargo | 21/3/15 | 471
| 2207 | 0 | MEGGA P3 Junction Box | 2015-03-05 | riser balcony | prod | 2015-10-03
| 2203 | 0 | Change deck trolley batteries | 2015-03-05 | 5 | prod | 2015-08-03
| 2211 | 0 | Carry out electrical repairs on topsides main deck and external accomodation lighting | 2015-03-05 | topsides | prod | 2015-11-03
| 2212 | 0 | To carry out checks on MGCB suction scrubber LCV | 2015-03-05 | 72 | prod | 2015-05-03
7345 |  | 0 | carry out electrical repairs on engine room lighting | 2015-03-05 | ER | maint | 2015-11-03
7346 |  | 0 | Carry out preservation on electrical motors | 2015-03-05 | topsides | prod | 2015-11-03
43183 |  | 0 | P3 spool and ESDV installation | 2015-03-05 | riser balcony | prod | 19/3/15 |  | 898 |  | 13a
| 2210 | 0 | Range verification on field instruments as in DCS and change if necessary - CO2 Comp A & B | 2015-03-05 | 73 | prod | 2015-07-03 | 477 / 478 / 479
| 35017 | 0 | Remove and re-instate temp prod in IGC A | 2015-03-05 | 76 | prod | 2015-08-03 |  | 40636 |  | 16a
43172 |  | 0 | Change over spool on suction of LP Service Pump - MDO/SW suply | 2015-03-05 | 5 | prod | 2015-11-03
43176 |  | 0 | Opening of false doors inside ENIF | 2015-03-05 | ENIF | UEA | 2015-12-03
43185 |  | 0 | Punctual painting retifier job on CPVC Pipe on main deck | 2015-03-05 | main deck | prod | 2015-07-03
| 35016 | 0 | Using pneumatic drill during pipe alignment on CO2 Comp | 2015-03-05 | 73 | prod | 2015-11-03
| 35032 | 0 | Check an energise the tank LG Lighting | 2015-03-05 | 62 | prod | 2015-07-03
| 34648 | 0 | loop checking on CO2 comp A | 2015-03-05 | 73 | prod | 2015-11-03 |  | 937 |  | 14b
43191 |  | 0 | Open cable cellar manholes and ventilate | 2015-03-05 | main deck | cargo | 2015-10-03
43188 |  | 0 | Install Honeywell Dyno metrics alarm and events collector software on OPC Server | 2015-03-05 | CCR | maint | 2015-06-03
| 2208 | 0 | Verification on field instruments MGC A 1 & 2 | 2015-03-05 | 71 | prod | 2015-08-03 | 474
| 2206 | 0 | Verification on field instruments IGC A & B | 2015-03-05 | 76 | prod | 2015-08-03 | 472
43166 |  | 0 | Removal and reinstall of mono block valve for inspection on MGC A T1 | 2016-03-05 | 71 | prod | 2015-06-03
| 2204 | 0 | Renew corroded flanged for forepeaak | 2015-03-05 | main deck | cargo | 2015-06-03
| 35044 | 0 | Install and checks on Riser balcony Instrumentation and tubing on P3 | 2015-03-06 | Riser balcony | prod | 2015-11-03 |  | 898 / 881 |  | 13b
| 2209 | 0 | To carry out range verification on field instrumentation in DCS | 2015-03-06 | 72 | prod | 2015-09-03 | 475 / 476
7344 |  | 0 | To attend to leaks on aft offloading SDV hydraulic tubing | 2015-03-06 | Poop deck | prod | 2015-06-03
43179 |  | 0 | Connect and disconnect umbilical hoses on TUTU Plate of P3 | 2015-03-06 | Riser balcony | prod | 21/3/15
4024 |  | 0 | AMOS Sewage Plant inspection | 2015-03-06 | ER | maint | 2015-06-03 |  | 52 |  | 6
43194 |  | 0 | Install and test Netherlocks on P4 Pig Launcher and reiever | 2015-03-06 | 266 | prod | 2015-09-03
| 35027 | 0 | Check electrical conductivity between vessel and seawater | 2015-03-07 | main deck | cargo | 2015-12-03
| 35036 | 0 | Use of non ex rated test equipment & 220V source to simulate vibration on CO2 comp A | 2015-03-07 | 73 | prod | 16/3/15
| 34669 | 0 | Check the termination of the RIO Panel for IGC A | 2015-03-07 | 76 | prod | 2015-06-03
| 35035 | 0 | Use of the camera | 2015-03-07 | topsides | prod | 2015-12-03 |  |  |  |  | hwp 34692
43210 |  | 0 | Conduct replacement of opening lever mechanism circuit breaker Process SWBD HV/LV Transformer | 2015-03-07 | ENIF | UEA | 2015-07-03 |  | 282 |  | 1a
7348 |  | 0 | To carry out general repairs in accom, gally and laundry | 2015-03-07 | accom | cargo | 15/3/15 |  |  |  |  | cwp 0707
| 34668 | 0 | Use of the camera | 2015-03-07 | topsides | prod | 2015-12-03 |  |  |  |  | hwp 34692
4026 |  | 0 | Inspection and cleaning of FWD central cooler | 2015-03-07 | ER | maint | 2015-07-03 |  | 53 |  | 16a
42957 |  | 0 | Chemical decanting | 2015-03-07 | 75 | prod | 2015-09-03
43192 |  | 0 | Cleaning drain boxes | 2015-03-07 | topsides | prod | 13/03/15 |  |  |  |  | cwp 43270
| 34671 | 0 | Camera | 2015-03-07 | topsides | prod | 13/3/15 |  |  |  |  | hwp 34698
43190 |  | 0 | Entry into cable celler | 2015-03-07 | main deck | cargo | 21/3/15 |  |  | 43190/1
43187 |  | 0 | Replace light in lab fume cabinet | 2015-03-07 | lab | prod | 2015-07-03
43227 |  | 0 | Remove shacke from FWD hawser messenger and install back | 2015-03-07 | 63 / 71 | prod | 2015-08-03 | 43227
43224 |  | 0 | Scaffolding | 2015-03-08 | topsides | prod | 18/3/15
7349 |  | 0 | Check and renew temp control in fish and veg room :-) | 2015-03-08 | accom | cargo | 2015-08-03
| 2213 | 0 | Check I/O Fail alarm on VRU T71PSI7126 | 2015-03-08 | 75 | prod | 2015-08-03 | 298
| 2214 | 0 | Hot work in mechanical shop | 2015-03-08 | sunken deck | maint | 14/3/15
| 34670 | 0 | Check and energize tank level guage sight glass lighting | 2015-03-08 | 75 | prod | 2015-12-03
43193 |  | 0 | Lifeboat AMOS routines | 2015-03-08 | lifeboats | cargo | 14/3/15 | V001
| 35048 | 0 | Valve stoking of BDV's on CO2 Comp B | 2015-03-08 | 73 | prod | 2015-08-03 |  | 936 |  | 11c
43169 |  | 0 | Tubing installation on analyzers | 2015-03-08 | 78 | prod | 2015-09-03
43170 |  | 0 | Removal of valve actuator for inspection | 2015-03-08 | 73 | prod | 2015-11-03 |  | 349 |  | 1
| 35050 | 0 | Stroking of BDV's on H2S package | 2015-03-08 | 79 | prod | 2015-09-03
43232 |  | 0 | wind socks | 2015-03-08 | accom | cargo | 2015-08-03
43199 |  | 0 | Lube oil circulation of CO2 A | 2015-03-08 | 73 | prod | 15/3/15 |  |  |  |  | cwp 40568
43222 |  | 0 | Lube oil circulation of CO2 B | 2015-03-08 | 73 | prod | 15/3/15 |  |  |  |  | cwp 40567
43230 |  | 0 | Commissioning of subsea control systems by one subsea | 2015-03-09 | ENIF | UEA | 15/3/15 |  |  |  |  | cwp 40600
43225 |  | 0 | Commissioning of DGS on CO2 Comp A | 2015-03-09 | 73 | prod | 15/3/15 |  | 937 |  | 14a | cwp 40580
| 2598 | 0 | F&G routines on 266 | 2015-03-09 | 266 | prod | 2015-09-03 | 482
| 2205 | 0 | Range verification on field instruments | 2015-03-09 | 74 | prod | 2015-09-03 | 473
| 35018 | 0 | Valve function checks on MGC B -1 | 2015-03-09 | 72 | prod | 15/3/15
43198 |  | 0 | Pressure testing tubing on CO2 comp A&B | 2015-03-09 | 73 | prod
| 35034 | 0 | Voltage, current and temp measurement on heat tracing on refrigerant package | 2015-03-09 | 74 | prod | 2015-12-03
43231 |  | 0 | Sample P2 | 2015-03-09 | 267 | prod | 15/3/15 |  |  |  |  | cwp 43280
43235 |  | 0 | Dive ops | 2015-03-09 | riser balcony | prod | 16/3/15 |  | 40620 |  | 3 | cwp 43281
4027 |  | 0 | Chloropac AMOS routines | 2015-03-09 | ER | maint | 2015-10-03 |  | 201 |  | 17a
| 34672 | 0 | Running IKM Liquid N2 HE test equipment | 2015-03-09 | fwd laydown | prod | 15/3/15 | 293 |  |  |  | hwp 34704
| 2597 | 0 | F& Gas routine AMOS testing | 2015-03-09 | 265 | prod | 2015-10-03 | 481
| 34675 | 0 | Chipping and painting | 2015-03-09 | topsides | prod | 18/3/15
7347 |  | 0 | Electrical repairs in accom | 2015-03-10 | accom | cargo | 16/3/15 |  |  |  |  | cwp 6711
7350 |  | 0 | Install volume tank and modfy tubing on FWD Battery room dampers | 2015-03-10 | Forecastle | UEA | 21/3/15 | 484
6701 |  | 0 | Checks on level switches for chlorine dosing | 2015-03-10 | ER | maint | 2015-10-03
| 34682 | 0 | Painting and pictures | 2015-03-10 | all | cargo | 19/3/15
| 2596 | 0 | F&G AMOS checks | 2015-03-10 | 267 | prod | 2015-10-03 | 485
40558 |  | 0 | Termination of netherlock cables for UCP - CO2 Comp A | 2015-03-10 | ENIF | UEA | 15/3/15
40559 |  | 0 | Termination of netherlock cables for UCP - CO2 Comp B | 2015-03-10 | ENIF | UEA | 15/3/15
| 34676 | 0 | Check and calibrate PT on Pig launcher P4 | 2015-03-10 | 266 | prod | 2015-12-03 |  | 320 |  | 4 | LTI 20
43256 |  | 0 | Tubing installation on CO2 comp A & B | 2015-03-10 | 73 | prod | 16/3/15 |  | 937 |  | 14c | hwp 34648
43254 |  | 0 | Pipe alignment on CO2 Comp B | 2015-03-10 | 73 | prod |  |  | 930 |  | 11a
43261 |  | 0 | Repair leak on valve body plug on IGC A Scrubber drain | 2015-03-10 | 76 | prod | 2015-11-03 |  | 920 |  | 16
| 34681 | 0 | Inspection and checks of FWD ARTIMIS antena panel | 2015-03-10 | Forecastle | cargo | 14/3/15
4028 |  | 0 | AMOS Maintenance on Instrument air comp #4 | 2015-03-10 | ER | maint | 2015-10-03 |  | 202 |  | 6a
| 2599 | 0 | F&G AMOS checks | 2015-03-10 | 264 | prod | 2015-10-03 | 486
43264 |  | 0 | Removing of Hellan strainers drain valves for inspection on MGC A -2 | 2015-03-11 | 71 | prod | 2015-12-03 |  | 152 |  | 6
| 34680 | 0 | Use of pneumatic drill and saw on CO2 Comp Train B for pipe alignment | 2015-03-11 | 73 | prod
| 34678 | 0 | carry out functional test of MGC A -2 PCV and FCV | 2015-03-11 | 71 | prod | 19/3/15
| 34701 | 0 | Check calibration of LT2105 on MGC A -2 | 2015-03-11 | 71 | prod | 2015-11-03
| 2218 | 0 | Carry out checks on instruments loops at topsides for wire checks - as per list | 2015-03-11 | topsides | prod | 15/3/15 | 488
| 2600 | 0 | F&G AMOS checks | 2015-03-11 | 11 | prod | 2015-11-03 | 487
| 2219 | 0 | F&G AMOS checks | 2015-03-11 | 11 & 12 | prod | 2015-11-03 | 490
| 2220 | 0 | F&G AMOS checks | 2015-03-11 | 005 / 62 | prod | 2015-11-03 | 489
40551 |  | 0 | Manual cargo handling | 2015-03-11 | topsides | cargo | 17/3/15
6703 |  | 0 | Replace N2 actuated valve release disk on GT#1 mist fire fighting | 2015-03-11 | 12 | maint | 2015-11-03
40554 |  | 0 | Terminate interlock cables in UCP for MGC B -1 Netherlock panel | 2015-03-11 | ENIF | UEA | 17/3/15
40553 |  | 0 | Terminate interlock cables in UCP for MGC A -2 Netherlock panel | 2015-03-11 | ENIF | UEA | 17/3/15
6702 |  | 0 | Cranes weekly inspection | 2015-03-11 | crane | cargo | 13/03/15
43265 |  | 0 | Pump Room Entry | 2015-03-11 | Pump Room | prod | 21/3/15 |  |  | 43265/1
6704 |  | 0 | Replace duplex MDO filters on turbines | 2015-03-12 | main deck | cargo | 13/03/15
4030 |  | 0 | Fitting of pull wires on ER fan dampers | 2015-03-12 | funnel deck | maint | 14/3/15
| 2225 | 0 | F&G AMOS Routines | 2015-03-12 | 71 / 75 | prod | 2015-12-03 | 493
| 34686 | 0 | Rotational checks of CO2 comp hydraulic starting pump | 2015-03-12 | 73 | prod | 22/3/15
| 35009 | 0 | Check and energise level guage lighting | 2015-03-12 | 63 | prod | 13/03/15
6705 |  | 0 | Carry out preservatioon on electrical motors | 2015-03-12 | topsides | prod | 18/3/15
| 2226 | 0 | Lighting repair on topsides | 2015-03-12 | topsides | prod | 18/3/15
43257 |  | 0 | Interlock system function check on export gas pig launcher | 2015-03-12 | 63 | prod | 2015-12-03
| 35021 | 0 | Check solenoid valve for T75-SDV-1136 on IGC A | 2015-03-12 | 75 | prod | 13/03/15
| 35020 | 0 | Carry out functional checks on T71-PCV-1124 MGC A - 1 | 2015-03-12 | 71 | prod | 18/3/15
| 35019 | 0 | Loop checks and valve stroking on CO2 Comp A | 2015-03-12 | 73 | prod |  |  | 937 |  | 14b | hwp 34720
43197 |  | 0 | Run compressors with overides | 2015-03-12 | 71 / 72 / 76 | prod | 18/3/15 | 789 / 285 |  |  |  | cwp 43293
43221 |  | 0 | Rope access on topsides | 2015-03-12 | topsides | prod | 18/3/15 |  |  |  |  | cwp 40587
43195 |  | 0 | Setting up IKM Equipment | 2015-03-12 | fwd laydown | prod | 18/3/15
| 2224 | 0 | F&G AMOS Routines | 2015-03-12 | 63 / 73 | prod | 2015-12-03 | 492
| 2221 | 0 | Investigate cross loop of P3 / P5 Pig launcher PT's | 2015-03-12 | 266 | prod | 2015-12-03
43266 |  | 0 | Charging BA and escape sets cylinders in ERT's | 2015-03-12 | accom | cargo | 21/3/15
43272 |  | 0 | Painting at emergency gen room | 2015-03-12 | emer gen | maint | 16/3/15
| 2223 | 0 | F&G AMOS Routines | 2015-03-12 | 74 / 78 | prod | 15/3/15 | 491
4022 |  |  | rust removing and painting in ER | 2015-04-03 | ER | maint | 2015-12-03
43182 |  |  | install and remove bottom spool, sheave p3 and p4 SLWR | 2015-06-03 | riser balcon | prod | 2015-12-03 |  |  |  |  | cwp 43268
| 34684 | 0 | Fault find on Lube oil Heater on Refridge comp | 2015-03-13 | 74 | prod | 20/3/15 |  | 1239 |  | 1a
| 34685 | 0 | Replacement of heat tracing thermostat | 2015-03-13 | 78 | prod | 15/3/15 |  | 1238 |  | 15a
43229 |  | 0 | SWLP Pulling | 2015-03-13 | Riser Balcony | prod | 18/3/15
43259 |  | 0 | Charge N2 Bottles | 2015-03-13 | 22 | prod | 20/3/15
4031 |  | 0 | Tighten Rudder locking mechanism | 2015-03-13 | ER | maint | 14/3/15
| 34691 | 0 | Check and calibrate Level transmitters on MGC B -1 scrubbers | 2015-03-13 | 72 | prod | 19/3/15 | 34691
| 34702 | 0 | Loop checking on heat detectors | 2015-03-13 | 72 | prod | 19/3/15
| 35022 | 0 | Use of pneumatic drill | 2015-03-13 | 73 | prod | 19/3/15
| 2223 | 0 | F&G Amos inspections | 2015-03-13 | 74 / 78 | prod |  | 491
| 2228 | 0 | Fire damper routines on GT #2 - offline | 2015-03-13 | 12 | prod | 14/3/15 | 496
| 2230 | 0 | F&G Amos inspections | 2015-03-13 | 76 / 79 | prod | 13/03/15 | 495
| 2229 | 0 | F&G Amos inspections | 2015-03-13 | 72 / 77 | prod | 13/03/15 | 497 / 498
43228 |  | 0 | dive ops | 2015-03-13 | Riser Balcony | prod | 13/03/15 |  | 40620 |  | 3
| 34690 | 0 | carry out check on probes on GT#2 | 2015-03-13 | TS 12 | maint | 15/3/15 | 101
| 35010 | 0 | Check and energise tank level guages | 2015-03-14 | 77 | prod | 18/3/15
| 34694 | 0 | Trouble shoot MGC B - 1 2nd stage discharge PST4226 | 2015-03-14 | 72 | prod | 15/3/15 | 34694
| 35011 | 0 | Cable pulling and termination of the 230V power supply for CO2 Comp Rio Panel | 2015-03-14 | 73 | prod | 19/3/15
40567 |  | 0 | Clean up circulation of CO2 Comp B Lube oil | 2015-03-14 | 73 | prod | 20/03/2015 |  |  |  |  | 40586
40568 |  | 0 | Clean up circulation of CO2 Comp A Lube oil | 2015-03-14 | 73 | prod | 20/03/2015 |  |  |  |  | 40584
| 25000 | 0 | Loop check H2S Scav pump for ITR Scope | 2015-03-14 | 5 | prod
| 2227 | 0 | F&G Amos inspections | 2015-03-14 | Main Deck | cargo | 15/3/15 | 2227
43270 |  | 0 | Clean drain boc | 2015-03-14 | topsides | prod | 20/03/2015 |  |  |  |  | 43296
40569 |  | 0 | Lube oil leak repair on MGC B - 2 Motor NDE | 2015-03-14 | 72 | prod | 18/3/15 |  | 40639 |  | 4a
| 34699 | 0 | Remove and re-instate vibration and temp probe on MGC B - 2 NDE side | 2015-03-14 | 72 | prod | 16/3/15
4033 |  | 0 | Inspection of Jockey Pump A - Vibration | 2015-03-15 | ER | Maint | 18/03/2015 | 155 | 203 |  | 6a
40593 |  | 0 | Cleaning Hellan Strainer on MGC B -1 | 2015-03-15 | 71 | Prod | 16/3/15 |  | 803 |  | 16
40596 |  | 0 | Scafolding | 2015-03-15 | Topsides | Prod | 21/3/15 |  |  |  |  | cwp 40657
| 2234 | 0 | General activities in Workshop | 2015-03-15 | Sunken Deck | Maint | 21/3/15 |  |  |  |  | hwp 2249
6707 |  | 0 | Repairs in accom | 2015-03-15 | accom | Cargo | 21/3/15 |  |  |  |  | cwp 6720
6708 |  | 0 | Lighting in ER | 2015-03-15 | ER | Maint | 22/3/15
40600 |  | 0 | Commissioning Subsea Control Systems - P3 | 2015-03-15 | ENIF | Maint | 20/3/15
| 2231 | 0 | F&G Amos inspections | 2015-03-15 | 266 | Prod | 16/3/15 | 499 / 500
| 2233 | 0 | Verify Leak detection Level transmitter on cooler high points | 2015-03-15 | Topsides | Prod | 18/3/15
6706 |  | 0 | Trouble shoot fault indication on damper in ENIF | 2015-03-15 | ENIF | UEA | 15/3/15
| 34689 | 0 | Chipping and painting | 2015-03-15 | maindeck | Cargo | 21/3/15 |  |  |  |  | hwp 38731
40594 |  | 0 | Pressure test fire fighting skid on CO2 Comp A | 2015-03-15 | 73 | Prod | 16/3/15
| 34700 | 0 | Implement DCF 872 on riser PST5205 | 2015-03-15 | 267 | Prod | 18/3/15 | 34700
40574 |  | 0 | Top up water cylinders in fire fighting cabinet on CO2 Comp A | 2015-03-15 | 73 | Prod | 22/3/15
40580 |  | 0 | Installation of DGS on CO2 Comp A | 2015-03-15 | 73 | Prod | 16/3/15 |  | 937 |  | 14a | LOB 14
| 34698 | 0 | Camera | 2015-03-15 | topsides | Prod | 21/3/15 |  |  |  |  | hwp 34734
| 34704 | 0 | Running IKM Equipment | 2015-03-15 | FWD Laydown | Prod | 18/3/15
| 34692 | 0 | Camera | 2015-03-15 | Topsides | Prod | 21/3/15 |  |  |  |  | hwp 34735
43252 |  | 0 | Decant chemicals | 2015-03-15 | Topsides | Prod | 21/3/15 |  |  |  |  | cwp 40701
| 2236 | 0 | Replace internet switch in RIO panel | 2015-03-15 | Topsides | Maint | 15/3/15
43262 |  | 0 | cleaning of CM pump A strainer | 2015-03-15 | Topsides | Maint | 15/3/15 |  | 151 |  | 17
43280 |  | 0 | P2 Oil Sampling | 2015-03-16 | 267 | prod | 22/3/15 |  |  |  |  | cwp 40661
| 34711 | 0 | Painting andd taking pictures | 2015-03-16 | main deck | Cargo | 20/03/15
| 34710 | 0 | Check and calibrate and stroke IGC A Antisurge valve | 2015-03-16 | 76 | Prod | 20/3/15
| 34708 | 0 | Trouble shoot instrments during Refrig Compressor comissioning | 2015-03-16 | 74 | Prod | 22/3/15
40595 |  | 0 | Carry out modification on cable trays CO2 Comp A | 2015-03-16 | 73 | Prod | 18/3/15
43281 |  | 0 | Dive Operations | 2015-03-16 | Riser Balcony | Prod | 22/3/15 |  | 40620 |  | 3a | cwp 40656
| 34706 | 0 | Check and energise tank sight glass lights | 2015-03-16 | 71 | Prod | 19/3/15
| 34705 | 0 | Check and energise tank sight glass lights | 2015-03-16 | 74 | Prod | 19/3/15
| 34707 | 0 | Loop checks and B-ITR's on manifold modules | 2015-03-16 | manifolds | Prod | 19/3/15
40576 |  | 0 | Pipe alignment on CO 2 Comp A | 2015-03-16 | 73 | Prod | 22/3/15 |  | 937 |  | 14c | cwp 40575
40573 |  | 0 | Replacement of valves on CO2 Comp | 2015-03-16 | 73 | Prod | 18/3/15
43276 |  | 0 | Spool and ESDV Removal on I tube 18 (P4 Service Line) | 2015-03-16 | Riser Balcony | Prod | 22/3/15 |  | 43323 |  | 2 | LTI 20
40570 |  | 0 | Leak Repair on MGC B - 2 PSV5253 A & C (2nd Stage Discharge) | 2015-03-16 | 72 | Prod | 16/3/15 |  | 40638 / 801 |  | 4a | LTI 19
| 2232 | 0 | amos routines on F&G on TS 63 | 2015-03-16 | 63 | maint | 16/3/15 | 306/307/308/309
40592 |  | 0 | carry out pressure test on P3 service line | 2015-03-16 | 266 | prod | 16/3/15
40599 |  | 0 | repairs on P3 hydraulic lines (kinked) | 2015-03-16 | Riser Balcony | prod | 16/3/16
43273 |  | 0 | install and remove bleeing assembly on P3 | 2015-03-16 | Riser Balcony | maint | 16/3/17
| 34716 | 0 | Istall Sample tubing inside CO2 Turbione ventilation duct - include rope access | 2015-03-17 | 73 | prod | 22/3/15
43260 |  | 0 | Start-up refridge compressor | 2015-03-17 | 74 | prod | 22/3/15 | 43260 |  |  |  | cwp 40666
43282 |  | 0 | Top up refrigerant - R-134A | 2015-03-17 | 74 | prod | 22/3/15 |  |  |  |  | cwp 40667
| 34696 | 0 | Using pneumatic drill & saw in hazardous area - mod 73 | 2015-03-17 | 73 | prod | 22/3/15 |  |  |  |  | hwp 34737
| 34713 | 0 | Use of camera | 2015-03-17 | topsides | prod | 22/3/15 |  |  |  |  | hwp 34718
43284 |  | 0 | Dive Operations for pulling P4 Gas Lift | 2015-03-17 | Riser Balcony | prod | 22/3/15 |  | 40620 |  | 3b
6711 |  | 0 | Electrical repairs in accomodation | 2015-03-17 | accom | cargo | 22/3/15
6709 |  | 0 | Replace faulty control card in HVAC Unit | 2015-03-17 | ER | maint | 21/3/15 |  | 289 |  | 15a
| 2242 | 0 | Check Level transmitter calibrations on treater and Floatation vessel | 2015-03-17 | 62 / 63 | prod | 21/3/15 | 311
43283 |  | 0 | Riser Pilling - P4 Service | 2015-03-17 | Riser Balcony | prod | 19/3/15
0
| 2241 | 0 | Cell recording on UPS B Batteries | 2015-03-18 | UPS | Cargo | 18/3/15
| 2240 | 0 | Cell recording on UPS A Batteries | 2015-03-18 | UPS | cargo | 18/3/15
6714 |  | 0 | Repair Helideck lights | 2015-03-18 | helideck | cargo | 18/3/15
| 2239 | 0 | Carry out checks on COT#02 | 2015-03-18 | COT2 Wing STBD | cargo | 18/3/15
6712 |  | 0 | Weekly maintenance and grease of slew bearings | 2015-03-18 | cranes | cargo | 18/3/15
| 2235 | 2 | Remove turbine and flow meter on mod 68 | 2015-03-18 | 68 | cargo |  |  | 288 |  | 4
| 69 | 0 | Drilling holes in jockey pump A motor foot base | 2015-03-18 | ER | maint | 18/3/15
| 34719 | 0 | Rotation checks of CO2 Compressor B hydraulic start pump | 2015-03-18 | 73 | prod | 22/3/15
43289 |  | 1 | LV Cables from MTC to electrical panel check and identify | 2015-03-18 | ENIF | UEA
40587 |  | 2 | Rope access to remove loose items on topsides | 2015-03-18 | topsides | prod
43286 |  | 1 | Collect gas sample on Mod 74 | 2015-03-18 | 74 | prod |  | 43286
43184 |  | 2 | Manual Cargo Handling | 2015-03-18 | all areas | cargo
43291 |  | 2 | Adjust the seal gas system to PCV to optimize the flow MGC B #1 | 2015-03-18 | 72 | prod |  | 43291
43253 |  | 0 | Assembly of the ball valves on CO2 Comp B Scrubber | 2015-03-18 | 73 | prod | 18/3/15
43290 |  | 2 | Install pressure guage on IGC B Seal Gas System | 2015-03-18 | 76 | prod
| 2244 | 0 | Hotwork on sunken deck to install shelves | 2015-03-18 | suncken deck | prod | 21/3/15 | 312
| 2237 | 0 | carry out functional checks | 2015-03-18 | fwd fwp | maint | 18/3/15 | 310
40598 |  | 0 | displace 800 liters from P3 riser with N2 prior do the pressure test | 2015-03-18 |  | prod | 18/3/15
43292 |  | 0 | pigging ops on P3 | 2015-03-18 |  | prod | 18/3/15
43275 |  | 0 | N2/He leak test of P3 production riser | 2015-03-18 |  | prod | 18/3/15
6716 |  | 0 | Functional checks on fire damper and rectify faults | 2015-03-19 | accom | cargo | 20/3/15
| 2245 | 0 | Carry out function checks on fire dampers | 2015-03-19 | forecastle | cargo | 19/3/15
43287 |  | 0 | Pigging SPH-8 I-Tube 20 | 2015-03-19 | Riser Balcony | prod | 20/3/15
| 2247 | 2 | Test and energise treater transformer level switch | 2015-03-19 | 62 | prod
43285 |  | 0 | Lifeboats and FRC weekly inspection | 2015-03-19 | A Deck | cargo | 20/3/15 | 43285/1
| 34915 | 0 | Test Run CO2 Comp A Ventilation Fan | 2015-03-19 | 73 | prod | 22/3/15
43277 |  | 0 | Fault finding on the PMS | 2015-03-19 | ENIF | UEA | 21/3/15
| 2243 | 0 | Alter the steps for safe access to stbd side aft and use pneumatic drill | 2015-03-19 | main deck | prod | 22/3/15
| 34720 | 2 | Loop Checking and valve stroking on CO2 Compressor A | 2015-03-19 | 73 | prod |  |  | 937 |  | 14B
43295 |  | 0 | Download on F&G | 2015-03-19 | CCR | prod | 19/3/15
4034 |  | 0 | replace gasket on steam IG dump | 2015-03-19 | er | maint | 19/3/15
43269 |  | 0 | change spool on LP service pump | 2015-03-19 | 77 | prod | 19/3/15
| 35000 | 0 | flow transmitter loop check | 2015-03-19 | 5 | maint | 19/3/15
| 34723 | 1 | Use of Ofnonex rated refrigerant recovery equipment for commissioning | 2015-03-20 | 74 | prod
40586 |  | 1 | Clean up circulation of CO2 Comp B mineral lube oil system | 2015-03-20 | 73 | prod
40584 |  | 1 | Clean up circulation of CO2 Comp A mineral lube oil system | 2015-03-20 | 73 | prod
43298 |  | 0 | Fumigator product application | 2015-03-20 | accom | cargo | 20/3/15
4036 |  | 0 | Removing of Elastomeric couplin gfrom FWD Feed Pump for use in Jockey Pump A | 2015-03-20 | ER | maint | 20/3/15 |  | 203 / 40652 |  | 11a | de-isolation epm 203/ epm 40652 in LOB 17
43297 |  | 0 | To connect cables in MGC A -2 UCP | 2015-03-20 | ENIF | UEA | 22/3/15
43268 |  | 0 | install and remove bottom spool, sheave p3 and p4 SLWR | 15/03/15 | riser balcon | prod | 20/03/15
| 34688 | 0 | run WSP | 14/3/15 | 77 | prod | 20/3/15
43227 |  | 0 | gas sample | 2015-07-03 | 63/74 | prod | 20/3/15
4038 |  | 0 | Inspection and alignement of Jockey pump B | 2015-03-21 | ER | maint | 21/3/15 |  | 40653 |  | 4a
40657 |  | 1 | Scaffolding operation | 2015-03-21 | topsides | prod
6718 |  | 2 | Carry out weekly lifeboat checks | 2015-03-21 | A Deck | cargo |  | 318
40653 |  | 1 | Commissioning of subsea control panel by one subsea | 2015-03-21 | ENIF | UEA
4037 |  | 2 | Chemical Cleaning on FWG N1 Evaporator | 2015-03-21 | ER | maint | 23/3/15
40561 |  | 1 | Cable identification from MTC in foam room | 2015-03-21 | foam room | cargo
43300 |  | 1 | Cable identification from MTC in HPU room | 2015-03-21 | HPU Room | cargo
| 34727 | 1 | Modify tubing as per attached P&ID trouble shoot level transmitter T71LT4105 & 4104 | 2015-03-21 | 72 | prod |  | 34727 | 809
| 34724 | 2 | Replace level transmitter with SIL Approved level transmitter on LP Degasser | 2015-03-21 | 62 | prod | 23/3/15 | 34724 | 805 |  | 16
| 34726 | 2 | Check the calibration of the temp transmitters T67TIC2002 | 2015-03-21 | 74 | prod
| 34732 | 2 | Change faulty temp sensor in NDE bearing MGC B -1 | 2015-03-21 | 72 | prod | 23/3/15
40597 |  | 0 | Pressure test P3 hydraulics and ethanol line | 2015-03-21 | riser balcony | prod | 21/3/15
40575 |  | 1 | Pipe alignment on CO2 Comp A | 2015-03-22 | 73 | prod |  |  | 937 |  | 14C
40658 |  | 0 | Pull Cable from T62LST0411/0611 treater transformormer LST | 2015-03-22 | 62 | prod | 22/3/15
40660 |  | 1 | To pull cable from TS05 T28FT2634 | 2015-03-22 | 5 | prod | 23/3/15
| 34731 | 1 | Chipping and painting on main deck | 2015-03-22 | main deck | cargo
| 2250 | 0 | Check repair pressure transmitter on main gas A train 2 (T71PT2124) | 2015-03-22 | 71 | prod | 22/3/15
| 2249 | 1 | Carry out general activities in the workshop | 2015-03-22 | sunken deck | cargo
6720 |  | 1 | Carry out repairs in accomodation | 2015-03-22 | accom | cargo
6719 |  | 1 | Replace faulty socket outlet | 2015-03-22 | aft poop deck | cargo
| 34734 | 2 | Use of camera | 2015-03-22 | topsides | prod
43233 |  | 1 | Housekeeping, removal of not used cables, replacements of MCT's blocks | 2015-03-22 | cable cellar | cargo |  |  |  | 43233-2
6721 |  | 2 | Replace lube oil filter elements | 2015-03-22 | 72 | prod | 23/3/15
40651 |  | 2 | Install gasket on T24LST1206 upper flange on IGFU | 2015-03-22 | 63 | prod | 23/3/15 | 40651 |  | 808 | 16
43296 |  | 2 | Cleaning of drain boxes | 2015-03-22 | topsides | prod
40662 |  | 2 | Tandem mooring operations | 2015-03-22 | poop deck | cargo | 23/3/15
40659 |  | 1 | N2 Leak Test inside fire fighting skid of CO2 Comp A | 2015-03-23 | 73 | prod
40667 |  | 1 | Top up refrigerant unit using R-134A | 2015-03-23 | 74 | prod
| 34674 | 1 | Run new cables and terminate to UPS B distribition board | 2015-03-23 | 62 | prod
40663 |  | 1 | GSDV + spool installation I tube on P4 | 2015-03-23 | Riser balcony | prod |  |  | 43325 |  | 1
4039 |  | 1 | Inspection and cleaning of galley grease trap | 2015-03-23 | ER | maint |  |  | 55 |  | 11
40656 |  | 1 | Dive operations to remove the pulling head and install the spool on SLWR | 2015-03-23 | Riser balcony | prod |  |  | 40620 |  | 3
| 34718 | 1 | Camera - Rigging crew | 2015-03-23 | topsides | prod
| 34738 | 1 | Check and repair IO Failures on F&G Instruments | 2015-03-23 | topsides | prod |  | 1903151
| 34729 | 1 | paint inspection | 2015-03-23 | all areas | cargo | 23/3/15 |  |  |  |  | cancelled
| 34752 | 1 | cehck and repair TT on MGC T1 TSI 1132 | 2015-03-23 |  | maint | 23/3/15 | 2103151
40664 |  | 1 | fix Hydraulic leak on P3 HP1 and HP2 | 2015-03-23 | ss hpu | maint | 23/3/15 |  | 810
6717 |  | 1 | rectify leaks on Wag 5 | 2015-03-23 | Riser balcony | maint | 23/3/15 |  | 804
|  | 1 |  | 2015-03-23
|  | 1 |  | 2015-03-23